## in
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-10-18 | Requirements constraints | Yes | Completed | Requirements | N/A | 1
Vincent Chung | 2019-10-18 | List of foreseen risks | Yes | Completed | Risk analysis | N/A | 4
Mohammed Yaseen Jamal | 2019-10-18 | Description of non-functional user requirements | Yes | Completed | Requirements | N/A | 2
Ram Attra | 2019-10-18 | Description of functional user requirements | Yes | Completed | Requirements | N/A | 2
Eoghann Gibson | 2019-10-18 | Budget breakdown (costs of each section) | No | Incomplete | Project Costing | N/A | 0
Troy Greenaway | 2019-10-18 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-10-25 | Which software to use and gaant chart draft | Yes | Ongoing | Project Decision and Planning | N/A | 3
Vincent Chung | 2019-10-25 | Complete First Draft of Risk Analysis | Yes | Ongoing | Risk Analysis | N/A | 2
Mohammed Yaseen Jamal | 2019-10-25 | Complete First Draft of Requirements | Yes | Ongoing | Requirements | N/A | 8
Ram Attra | 2019-10-25 | Rough Draft of Project Costing | Yes | Ongoing | Project Costing | N/A | 2
Eoghann Gibson | 2019-10-25 | N/A | N/A | N/A | N/A | N/A | 0
Troy Greenaway | 2019-10-25 | Introduction, Test Plan for Usability | No | Incomplete | Usability | Requirements | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-11-01 | First draft of Project Decision and Planning | Yes | Ongoing | Project Decision and Planning | N/A | 4
Vincent Chung | 2019-11-01 | First draft of Risk Analysis | Yes | Ongoing | Risk Analysis | N/A | 1
Mohammed Yaseen Jamal | 2019-11-01 | First draft of Requirements | Yes | Ongoing | Requirements | N/A | 2
Ram Attra | 2019-11-01 | First draft of Project Costing | Yes | Ongoing | Project Costing | N/A | 1
Eoghann Gibson | 2019-11-01 | N/A | N/A | N/A | N/A | N/A | 0
Troy Greenaway | 2019-11-01 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-11-08 | First draft of Project Decision and Planning | Yes | Completed | Project Decision and Planning | N/A | 1
Vincent Chung | 2019-11-08 | First draft of Risk Analysis | Yes | Completed | Risk analysis | N/A | 1
Mohammed Yaseen Jamal | 2019-11-08 | First draft of Requirements | Yes | Completed | Requirements | N/A | 12
Ram Attra | 2019-11-08 | First draft of Project Costing | Yes | Completed | Project Costing | N/A | 2
Eoghann Gibson | 2019-11-08 | N/A | N/A | N/A | N/A | N/A | 0
Troy Greenaway | 2019-11-08 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-11-15 | 2nd draft of Project Planning | Yes | Ongoing | Project decision and planning | N/A | 3
Vincent Chung | 2019-11-15 | 2nd draft of Risk Analysis | Yes | Ongoing | Risk analysis | N/A | 0.5
Mohammed Yaseen Jamal | 2019-11-15 | 2nd draft of Requirements | Yes | Ongoing | Requirements | N/A | 4
Ram Attra | 2019-11-15 | 2nd draft of Project Costing | Yes | Completed | Project Costing | N/A | 1
Eoghann Gibson | 2019-11-15 | Complete mockup design (paper) | Yes | Completed | Usability evaluation | Requirements | 2
Troy Greenaway | 2019-11-15 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-11-22 | 2nd draft of Project planning | Yes | Complete | Project Decision and Planning | N/A | 4
Vincent Chung | 2019-11-22 | 2nd draft of Risk Analysis | Yes | Complete | Risk analysis | N/A | ?
Mohammed Yaseen Jamal | 2019-11-22 | 2nd draft of Requirements | Yes | Complete | Requirements | N/A | 4
Ram Attra | 2019-11-22 | Usability survey and report | Yes | Ongoing | Project Costing | Requirements | ?
Eoghann Gibson | 2019-11-22 | Complete mockups and report | Yes | Ongoing | Usability evaluation | Requirements | ?
Troy Greenaway | 2019-11-22 | N/A | N/A | N/A | N/A | N/A
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2019-11-29 | FIN | FIN | FIN | FIN | FIN | 0
Vincent Chung | 2019-11-29 | FIN | FIN | FIN | FIN | FIN | 0
Mohammed Yaseen Jamal | 2019-11-29 | Finalise stage 1 report | Yes | Yes | Stage 1 report | Requirements, Usability, Project Costing, Project Decision and Planning, Risk Analysis | 6
Ram Attra | 2019-11-29 | Complete usability report | Yes | Yes | Usability | Requirements | ?
Eoghann Gibson | 2019-11-29 | Complete usability report | Yes | Yes | Usabiliity | Requirements | ?
Troy Greenaway | 2019-11-29 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2020-01-23 | Backend side of F-UR 3 | Yes | Ongoing | F-UR 3 | Database | 3
Vincent Chung | 2020-01-23 | Frontend side of F-UR 1 | Yes | Complete | F-UR 1 | N/A | 15
Mohammed Yaseen Jamal | 2020-01-23 | Backend side of F-UR 1 and database schema | Yes | Complete | F-UR 1 | N/A | 12
Ram Attra | 2020-01-23 | Frontend side of F-SR 1 | Yes | Ongoing | F-SR 1 | N/A | 7
Eoghann Gibson | 2020-01-23 | Frontend side of F-UR 3 | No | Not delivered | F-UR 4 | N/A | 0
Troy Greenaway | 2020-02-23 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2020-01-30 | Backend side of F-UR 3 | Yes | Ongoing | F-UR 3 | Database | 10
Vincent Chung | 2020-01-30 | Landing page, home internal conditions page | Yes | Ongoing | F-UR 1 | N/A | 2
Mohammed Yaseen Jamal | 2020-01-30 | Energy breakdown page, refine register/login, and backend of energy page | Yes | Complete | F-UR 1 | N/A | 20
Ram Attra | 2020-01-30 | F-SR 1 | Yes | Ongoing | F-SR 1 | Backend | 15
Eoghann Gibson | 2020-01-30 | Frontend side of F-UR 4 and device timeline page | No | Not delivered | F-UR 4 | N/A | 0
Troy Greenaway | 2020-01-30 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2020-02-03 | Backend side of F-UR 3 | Yes | Ongoing | F-UR 3 | Database | 10
Vincent Chung | 2020-02-03 | Landing page, home internal conditions page | Yes | Ongoing | F-UR 1 | N/A | 2
Mohammed Yaseen Jamal | 2020-02-03 | Device activity, device timeline, connect app/server energy page | Yes | Complete | F-UR 3 | N/A | 20
Ram Attra | 2020-02-03 | F-SR 1 | Yes | Ongoing | F-SR 1 | Backend | 15
Eoghann Gibson | 2020-02-03 | N/A | N/A | N/A | N/A | N/A | 0
Troy Greenaway | 2020-02-03 | N/A | N/A | N/A | N/A | N/A | 0
Name | Week ending date | Objective | Satisfactory Progress | Progress | Deliverables | Dependencies | Hours
Lee Donovan | 2020-02-13 | Unit tests for current backend functionality | ? | ? | ? | N/A | ?
Vincent Chung | 2020-02-13 | Navigation flow chart, refactoring frontend | ? | ? | ? | N/A | ?
Mohammed Yaseen Jamal | 2020-02-13 | Progress report, ER Diagram | ? | ? | ? | UML diagrams | ?
Ram Attra | 2020-02-13 | F-SR 1 | ? | ? | ? | N/A | ?
Eoghann Gibson | 2020-02-13 | ? | ? | ? | ? | ? | ?
Troy Greenaway | 2020-02-13 | N/A | N/A | N/A | N/A | N/A | 0